## R1
Task # | Iteration | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | % Progress | Task Owner
1 | R1 - I1 | 05. Payment Gateway | 5.02 | Validate Payment | Implement GUI to validate payment with fields of address for billing | 2023-09-29 | 2023-10-06 | 100% | Swayambhu Duri, Tom Alex
2 | R1 - I1 | 05. Payment Gateway | 5.02 | Validate Payment | Implement API to connect to card companies for validation | 2023-09-29 | 2023-10-06 | 100% | Tom Cookson
3 | R1 - I1 | 05. Payment Gateway | 5.02 | Validate Payment | Implement exception handling if payment information does not validate | 2023-09-29 | 2023-10-06 | 100% | Swayambhu Duri
4 | R1 - I1 | 05. Payment Gateway | 5.02 | Validate Payment | Crosscut -In System Interface (inbound) | 2023-09-29 | 2023-10-06 | 100% | Swayambhu Duri
5 | R1 - I1 | 05. Payment Gateway | 5.02 | Validate Payment | Create test cases for validation | 2023-09-29 | 2023-10-06 | 100% | Srija Reddy, Ruchi Sharma
6 | R1 - I1 | 05. Payment Gateway | 5.01 | Define Payment Method | Implememt GUI with option of payment methods | 2023-10-07 | 2023-10-14 | 100% | Shubham Mittal
7 | R1 - I1 | 05. Payment Gateway | 5.01 | Define Payment Method | Use API for card payment | 2023-10-07 | 2023-10-14 | 100% | Tom Cookson
8 | R1 - I1 | 05. Payment Gateway | 5.01 | Define Payment Method | Implement security feature to protect customer card information | 2023-10-07 | 2023-10-14 | 100% | Swayambhu Duri, Shubham Mittal
9 | R1 - I1 | 05. Payment Gateway | 5.01 | Define Payment Method | Crosscut - Data-Driven Defaults | 2023-10-07 | 2023-10-14 | 100% | Tom Cookson, Tom Alex
10 | R1 - I1 | 05. Payment Gateway | 5.01 | Define Payment Method | Adding the stripe ID fields | 2023-10-07 | 2023-10-14 | 100% | Swayambhu Duri
11 | R1 - I1 | 05. Payment Gateway | 5.01 | Define Payment Method | Crosscut -In System Interface (inbound) | 2023-10-07 | 2023-10-14 | 100% | Swayambhu Duri
12 | R1 - I1 | 05. Payment Gateway | 5.01 | Define Payment Method | Create test cases for functionality and validation | 2023-10-07 | 2023-10-14 | 100% | Tom Cookson, Tom Alex
13 | R1 - I1 | 05. Payment Gateway | 5.01 | Define Payment Method | Execute test cases | 2023-10-07 | 2023-10-14 | 100% | Chetan Basnet
14 | R1 - I2 | 04. Advertising Management | 4.01 | Create Ad | Implement a GUI to upload ads | 2023-10-20 | 2023-10-27 | 100% | Swayambhu Duri
15 | R1 - I2 | 04. Advertising Management | 4.01 | Create Ad | Implement exceptional handling for large files | 2023-10-20 | 2023-10-27 | 100% | Suruchi Patil
16 | R1 - I2 | 04. Advertising Management | 4.01 | Create Ad | Create a button to display ad to targeted parking lot users | 2023-10-20 | 2023-10-27 | 100% | Swayambhu Duri, Shubham Mittal
17 | R1 - I2 | 04. Advertising Management | 4.01 | Create Ad | Crosscut - Entitlements External | 2023-10-20 | 2023-10-27 | 100% | Shubham Mittal
18 | R1 - I2 | 04. Advertising Management | 4.01 | Create Ad | Adding ads in to the Database model | 2023-10-20 | 2023-10-27 | 100% | Tom Alex
19 | R1 - I2 | 04. Advertising Management | 4.01 | Create Ad | Create test cases for functionality and validation | 2023-10-20 | 2023-10-27 | 100% | Chetan Basnet
20 | R1 - I2 | 04. Advertising Management | 4.01 | Create Ad | Execute test cases | 2023-10-20 | 2023-10-27 | 100% | Tom Cookson
21 | R1 - I2 | 04. Advertising Management | 4.02 | Modify Ad | Implement to button to change exisitng ad | 2023-10-20 | 2023-10-27 | 100% | Chetan Basnet
22 | R1 - I2 | 04. Advertising Management | 4.02 | Modify Ad | Delete ads | 2023-10-20 | 2023-10-26 | 100% | Tom Cookson
23 | R1 - I2 | 04. Advertising Management | 4.02 | Modify Ad | Implement to button to change target audience | 2023-10-20 | 2023-10-27 | 100% | Tom Cookson
24 | R1 - I2 | 04. Advertising Management | 4.02 | Modify Ad | Implement to button to delete ad | 2023-10-20 | 2023-10-27 | 100% | Swayambhu Duri
25 | R1 - I2 | 04. Advertising Management | 4.02 | Modify Ad | Crosscut - Entitlements External | 2023-10-20 | 2023-10-27 | 100% | Shubham Mittal
26 | R1 - I2 | 04. Advertising Management | 4.02 | Modify Ad | Create test cases for concurrency | 2023-10-20 | 2023-10-27 | 100% | Tom Alex
27 | R1 - I2 | 04. Advertising Management | 4.02 | Modify Ad | Execute test cases | 2023-10-20 | 2023-10-27 | 100% | Tom Cookson
28 | R1 - I2 | 04. Advertising Management | 4.03 | View Ad Statistics | Implement a API to note number clicks on ad | 2023-10-27 | 2023-11-03 | 100% | Tom Cookson
29 | R1 - I2 | 04. Advertising Management | 4.03 | View Ad Statistics | Implement a GUI to see number of clicks on ad | 2023-10-27 | 2023-11-03 | 100% | Swayambhu Duri
30 | R1 - I2 | 04. Advertising Management | 4.03 | View Ad Statistics | Implement a API gather useful information from ad | 2023-10-27 | 2023-11-03 | 100% | Srija Reddy, Ruchi Sharma
31 | R1 - I2 | 04. Advertising Management | 4.03 | View Ad Statistics | Implement a GUI to display ad statistics in insighful manner | 2023-10-27 | 2023-11-03 | 100% | Suruchi Patil
32 | R1 - I2 | 04. Advertising Management | 4.03 | View Ad Statistics | Crosscut - Entitlements External | 2023-10-27 | 2023-11-03 | 100% | Tom Alex
33 | R1 - I2 | 04. Advertising Management | 4.03 | View Ad Statistics | Create test cases for concurrency | 2023-10-27 | 2023-11-03 | 100% | Tom Cookson
34 | R1 - I2 | 04. Advertising Management | 4.03 | View Ad Statistics | Execute test cases | 2023-10-27 | 2023-11-03 | 100% | Chetan Basnet
35 | R1 - I2 | 02. Parking Lot Management | 2.01 | Track Occupancy | Implement image recognition and deep learningt to mark parking space as available or occupied | 2023-10-27 | 2023-11-03 | 100% | Suruchi Patil
36 | R1 - I2 | 02. Parking Lot Management | 2.01 | Track Occupancy | Make GUI for parking lot managers to access | 2023-10-27 | 2023-11-03 | 100% | Ruchi Sharma
37 | R1 - I2 | 02. Parking Lot Management | 2.01 | Track Occupancy | Create a button to access different parking lot | 2023-10-27 | 2023-11-03 | 100% | Suruchi Patil
38 | R1 - I2 | 02. Parking Lot Management | 2.01 | Track Occupancy | Implement a feature to send edge cases back to neural net for improvement | 2023-10-27 | 2023-11-03 | 100% | Tom Cookson
39 | R1 - I2 | 02. Parking Lot Management | 2.01 | Track Occupancy | Crosscut: Calculation, Crosscut: Entitlement, | 2023-10-27 | 2023-11-03 | 100% | Tom Cookson
40 | R1 - I2 | 02. Parking Lot Management | 2.01 | Track Occupancy | Adding images, cameras and lots table to the Database | 2023-10-27 | 2023-11-03 | 100% | Swayambhu Duri, Shubham Mittal
41 | R1 - I2 | 02. Parking Lot Management | 2.01 | Track Occupancy | Create test cases for functionality | 2023-10-27 | 2023-11-03 | 100% | Swayambhu Duri, Shubham Mittal
42 | R1 - I2 | 02. Parking Lot Management | 2.01 | Track Occupancy | Execute test cases | 2023-10-27 | 2023-11-03 | 100% | Tom Cookson, Tom Alex

## R2
Task # | Iteration | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | % Progress | Task Owner
1 | R2 - I1 | 03. Parking Lot Status | 3.01 | Search and Select Lot | Implement a GUI for users to select parking lot | 2023-11-03 | 2023-11-10 | 0% | Suruchi Patil
2 | R2 - I1 | 03. Parking Lot Status | 3.01 | Search and Select Lot | Implement API | 2023-11-03 | 2023-11-10 | 0% | Shubham Mittal
3 | R2 - I1 | 03. Parking Lot Status | 3.01 | Search and Select Lot | Implement core functionality | 2023-11-03 | 2023-11-10 | 0% | Tom Alex
4 | R2 - I1 | 03. Parking Lot Status | 3.01 | Search and Select Lot | Create test cases for Search and Select Lot functionlity | 2023-11-03 | 2023-11-10 | 0% | Tom Cookson
5 | R2 - I1 | 03. Parking Lot Status | 3.01 | Search and Select Lot | Execute test cases | 2023-11-03 | 2023-11-10 | 0% | Chetan Basnet
6 | R2 - I1 | 03. Parking Lot Status | 3.02 | View Occupancy | Implement core functionality | 2023-11-03 | 2023-11-10 | 0% | Swayambhu Duri, Shubham Mittal
7 | R2 - I1 | 03. Parking Lot Status | 3.02 | View Occupancy | Implement GUI requirments | 2023-11-03 | 2023-11-10 | 0% | Tom Cookson, Tom Alex
8 | R2 - I1 | 03. Parking Lot Status | 3.02 | View Occupancy | Show ads on screen | 2023-11-03 | 2023-11-10 | 0% | Swayambhu Duri, Tom Alex
9 | R2 - I1 | 03. Parking Lot Status | 3.02 | View Occupancy | Create test cases for View Occupancy functionality | 2023-11-03 | 2023-11-10 | 0% | Tom Cookson
10 | R2 - I1 | 03. Parking Lot Status | 3.02 | View Occupancy | Execute test cases | 2023-11-03 | 2023-11-10 | 0% | Chetan Basnet
11 | R2 - I1 | 03. Parking Lot Status | 3.03 | Access Occupancy Remotely | Create API for other website to use | 2023-11-10 | 2023-11-17 | 0% | Swayambhu Duri
12 | R2 - I1 | 03. Parking Lot Status | 3.03 | Access Occupancy Remotely | Implement core functionality | 2023-11-10 | 2023-11-17 | 0% | Suruchi Patil
13 | R2 - I1 | 03. Parking Lot Status | 3.03 | Access Occupancy Remotely | Create test cases for API functionality | 2023-11-10 | 2023-11-17 | 0% | Ruchi Sharma
14 | R2 - I1 | 03. Parking Lot Status | 3.03 | Access Occupancy Remotely | Execute test cases | 2023-11-10 | 2023-11-17 | 0% | Tom Cookson
15 | R2 - I2 | 02. Parking Lot Management | 2.02 | Access Footage Archive | Create GUI to access archieved footage | 2023-11-24 | 2023-12-01 | 0% | Suruchi Patil
16 | R2 - I2 | 02. Parking Lot Management | 2.02 | Access Footage Archive | Create cloud based system to store footage | 2023-11-24 | 2023-12-01 | 0% | Tom Cookson
17 | R2 - I2 | 02. Parking Lot Management | 2.02 | Access Footage Archive | Implement core functionality | 2023-11-24 | 2023-12-01 | 0% | Swayambhu Duri
18 | R2 - I2 | 02. Parking Lot Management | 2.02 | Access Footage Archive | Create GUI to select different parking lot | 2023-11-24 | 2023-12-01 | 0% | Suruchi Patil
19 | R2 - I2 | 02. Parking Lot Management | 2.02 | Access Footage Archive | Create test cases for access Footage Archive functionality | 2023-11-24 | 2023-12-01 | 0% | Swayambhu Duri, Shubham Mittal
20 | R2 - I2 | 02. Parking Lot Management | 2.02 | Access Footage Archive | Execute test cases | 2023-11-24 | 2023-12-01 | 0% | Swayambhu Duri, Tom Alex
21 | R2 - I2 | 02. Parking Lot Management | 2.03 | Detect Overparking | Implement API | 2023-12-08 | 2023-12-15 | 0% | Chetan Basnet
22 | R2 - I2 | 02. Parking Lot Management | 2.03 | Detect Overparking | Implement core functionality | 2023-12-08 | 2023-12-15 | 0% | Tom Cookson
23 | R2 - I2 | 02. Parking Lot Management | 2.03 | Detect Overparking | Implement notification functionality | 2023-12-08 | 2023-12-15 | 0% | Swayambhu Duri
24 | R2 - I2 | 02. Parking Lot Management | 2.03 | Detect Overparking | Create test cases for detect Overparking functionality | 2023-12-08 | 2023-12-15 | 0% | Srija Reddy, Ruchi Sharma
25 | R2 - I2 | 02. Parking Lot Management | 2.03 | Detect Overparking | Execute test cases | 2023-12-08 | 2023-12-15 | 0% | Tom Cookson
Formulas:
Start Date = [End Date]-7