## Initial Plan
Color Coding |  |  | Completed |  |  |  | SPRING 2023 SEMESTER
In Progress
[6 empty] | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[6 empty] | Date | 2023-01-29 | 2023-02-07 | 2023-02-12 | 2023-02-18 | 2023-02-26 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08
Project Phase | Activity |  | Task Owner Name | Start Date | End Date | Progress %
Project Initiation | Discussion of Business Case |  | Krunal Bhavsar | 2023-01-24 | 2023-01-29 | 100%
| Assigning Team Roles |  | Krunal Bhavsar | 2023-01-24 | 2023-01-29 | 100%
| Developing two Business Models |  | Krunal Bhavsar | 2023-01-24 | 2023-01-29 | 100%
| Documenting Project Initiation Document (PID) |  | Krunal Bhavsar | 2023-01-31 | 2023-02-07 | 100%
| Produce initial Project Plan, RACI |  | Swayambhu Dhuri | 2023-02-07 | 2023-02-12 | 100%
MILESTONE 1: INITIAL PROJECT PLAN COMPLETED
Requirements Definition | Produce BRM diagram, define User Roles |  | Shubham Mittal | 2023-02-14 | 2023-02-18 | 100%
| Produce Context Diagram, Define System Interfaces |  | Suruchi Patil | 2023-02-14 | 2023-02-18 | 100%
| Customer Needs |  | Tom Cookson | 2023-02-14 | 2023-02-18 | 100%
| Define Business Requirements |  | Tom Cookson | 2023-02-21 | 2023-02-26 | 100%
| Agree to System Requirements types |  | ALL | 2023-02-21 | 2023-02-26 | 100%
| Define Functional Decomposition & Fishbone Diagram |  | Shubham Mittal | 2023-02-21 | 2023-02-26 | 100%
| Produce RCT document |  | Tom Alex | 2023-02-21 | 2023-02-26 | 100%
| Decide which features to implement this semester |  | All | 2023-02-28 | 2023-03-07 | 100%
| Produce analysis diagrams (UML, DFD) |  | Tom Cookson, Chetan, Swaymbhu | 2023-04-11 | 2023-04-16 | 100%
| Define functional requirements (User Stories) |  | Krunal Bhavsar, Suruchi | 2023-04-11 | 2023-04-16 | 100%
| Update Project Plan with additional requirements tasks |  | Krunal | 2023-02-28 | 2023-03-07 | 100%
MILESTONE 2: REQUIREMENTS COMPLETED
Design | Architecture design (2 diagrams) |  | Swayambhu Dhuri | 2023-03-28 | 2023-04-16 | 100%
| Database Design (ERD, Table spec) |  | Tom Alex | 2023-03-28 | 2023-04-16 | 100%
| System Interface Design |  | Swayambhu Dhuri | 2023-03-28 | 2023-04-25 | 0%
| User interface design |  | Swayambhu Dhuri | 2023-04-06 | 2023-04-25 | 0%
| Class Diagram and Sequence Diagram |  | All | 2023-04-11 | 2023-04-17 | 100%
MILESTONE 3: DESIGN COMPLETED
Code | Create Account | GUI & Functionality Detailed Design | Swayambhu Dhuri | 2023-02-14 | 2023-03-07 | 100%
|  | Coding & Implemenation | Swayambhu Dhuri | 2023-02-28 | 2023-03-07 | 100%
| Create Entitlements | Create Entitlements per User Account Type | Swayambhu Dhuri | 2023-04-18 | 2023-04-25 | 100%
| Modify Account | GUI & Functionality Detailed Design | Swayambhu Dhuri | 2023-04-18 | 2023-04-25 | 50%
|  | Coding & Implemenation | Swayambhu Dhuri | 2023-04-18 | 2023-04-25 | 50%
| Cancel Account | GUI & Functionality Detailed Design | Swayambhu Dhuri | 2023-04-18 | 2023-04-25 | 50%
|  | Coding & Implemenation | Swayambhu Dhuri | 2023-04-18 | 2023-04-25 | 50%
| Account Summary | GUI & Functionality Detailed Design | Swayambhu Dhuri | 2023-04-18 | 2023-04-25 | 50%
|  | Coding & Implemenation | Swayambhu Dhuri | 2023-04-18 | 2023-04-25 | 50%
| Authenticate Account | GUI & Functionality Detailed Design | Swayambhu Dhuri | 2023-04-18 | 2023-04-25 | 50%
|  | Coding & Implemenation | Swayambhu Dhuri | 2023-04-18 | 2023-04-25 | 50%
MILESTONE 4: CODING COMPLETED
Integration & Testing | Plan testing, produce a Test Plan document |  | Tom Cookson | 2023-04-18 | 2023-04-25 | 100%
| Evaluate Features to be Tested |  | Tom Cookson | 2023-04-18 | 2023-05-08 | 0%
| Create Account | Execute Exploratory Testing | Tom Cookson | 2023-04-18 | 2023-05-08 | 0%
|  | Analyze Test Result | Tom Cookson | 2023-04-18 | 2023-05-08 | 0%
| Modify Account | Execute Exploratory Testing | Tom Cookson | 2023-04-18 | 2023-05-08 | 0%
|  | Analyze Test Results | Tom Cookson | 2023-04-18 | 2023-05-08 | 0%
| Cancel Account | Execute Exploratory Testing | Tom Cookson | 2023-04-18 | 2023-05-08 | 0%
|  | Analyze Test Result | Tom Cookson | 2023-04-18 | 2023-05-08 | 0%
| Account Summary | Execute Exploratory Testing | Tom Cookson | 2023-04-20 | 2023-05-08 | 0%
|  | Analyze Test Result | Tom Cookson | 2023-04-21 | 2023-05-08 | 0%
| Authenticate Account | Execute Exploratory Testing | Tom Cookson | 2023-04-18 | 2023-05-08 | 0%
|  | Analyze Test Result | Tom Cookson | 2023-04-18 | 2023-05-08 | 0%
MILESTONE 5: TESTING COMPLETED
Project Presentation | Prepare Application Demo for the Presentation |  | ALL | 2023-05-03 | 2023-05-09 | 0%
Note on B6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Fixed spelling of discussion, changed business model to Business Case