## Initial Plan
Color Coding |  | Completed |  |  |  | SPRING 2023 SEMESTER
In Progress
[5 empty] | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[5 empty] | Date | 2018-01-30 | 2018-02-06 | 2017-02-13 | 2018-02-20 | 2018-02-27 | 2018-03-06 | 2018-03-13 | 2018-03-20 | 2018-03-27 | 2018-04-03 | 2018-04-10 | 2018-04-17 | 2018-04-24 | 2018-05-01 | 2018-05-08
Project Phase | Activity | Task Owner Name | Start Date | End Date | Progress %
Project Initiation | Discussion of Business Case | Krunal Bhavsar | 2023-01-24 | 2023-01-29 | 100%
| Assigning Team Roles | Krunal Bhavsar | 2023-01-24 | 2023-01-29 | 100%
| Developing two Business Models | Krunal Bhavsar | 2023-01-24 | 2023-01-29 | 100%
| Documenting Project Initiation Document (PID) | Krunal Bhavsar | 2023-01-31 | 2023-02-07 | 80%
| Produce initial Project Plan, RACI | Swayambhu Dhuri | 2023-02-07 | 2023-02-12 | 80%
MILESTONE 1: INITIAL PROJECT PLAN COMPLETED
Requirements Definition | Produce BRM diagram, define User Roles | Ruchi Sharma | 2023-02-14 | 2023-02-19 | 0%
| Produce Context Diagram, Define System Interfaces | Swayambhu Dhuri | 2023-02-21 | 2023-02-26 | 0%
| Define Business Requirements | Chetan Besant | 2023-02-21 | 2023-02-26 | 0%
| Agree to System Requirements types | Swayambhu Dhuri | 2023-02-28 | 2023-03-07 | 0%
| Define Functional Decomposition | Krunal Bhavsar | 2023-02-28 | 2023-03-07 | 0%
| Produce RCT document | Krunal Bhavsar | 2023-02-28 | 2023-03-07 | 0%
| Decide which features to implement this semester | All | 2023-02-28 | 2023-03-07 | 0%
| Produce analysis diagrams (UML, DFD) | Krunal Bhavsar | 2023-04-11 | 2023-04-16 | 0%
| Define functional requirements (User Stories) | Krunal Bhavsar | 2023-02-28 | 2023-03-07 | 0%
| Update Project Plan with additional requirements tasks | Chetan Besant | 2023-02-28 | 2023-03-07 | 0%
MILESTONE 2: REQUIREMENTS COMPLETED
Design | Architecture design (2 diagrams) | Swayambhu Dhuri | 2023-03-28 | 2023-04-16 | 0%
| Database Design (ERD, Table spec) | Tom Alex | 2023-03-28 | 2023-04-16 | 0%
| System Interface Design | Swayambhu Dhuri | 2023-03-28 | 2023-04-25 | 0%
| User interface design | Swayambhu Dhuri | 2023-04-06 | 2023-04-25 | 0%
MILESTONE 3: DESIGN COMPLETED
Code | GUI & Functionality Detailed Design | TBD | 2023-02-07 | 2023-03-07 | 0%
| Establish code repository in GitHUb | TBD | 2023-02-07 | 2023-02-14 | 0%
| Coding & Implemenation | TBD | 2023-02-07 | 2023-03-07 | 0%
MILESTONE 4: CODING COMPLETED
Integration & Testing | Plan testing, produce a Test Plan document | TBD | 2023-04-18 | 2023-04-25 | 0%
| Evaluate Features to be Tested | TBD | 2023-04-18 | 2023-04-25 | 0%
| Design Test Cases | TBD | 2023-04-18 | 2023-04-25 | 0%
| Execute Test Cases | TBD | 2023-04-18 | 2023-04-25 | 0%
| Anaylze Test Results | ALL | 2023-04-18 | 2023-04-25 | 0%
MILESTONE 5: TESTING COMPLETED
Project Presentation | Prepare Application Demo for the Presentation | ALL | 2023-05-03 | 2023-05-09 | 0%
Note on B6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Fixed spelling of discussion, changed business model to Business Case