## Road Map
Quick Feed Application
|  |  | Release 1 |  | Release 2
Module | Core Feature Name | Story Points | Iteration 1 - 10/13/23 | Iteration 2 - 11/03/23 | Iteration 3 - 11/17/23 | Iteration 4 - 12/15/23
1. Account Management | 1.1 Summarize Account
1.2 Authenticate Account
1.3 Request Customer Support
1.4 Create Account
1.5 Modify Account
1.6 Cancel Account
2. Parking Lot Management | 2.1 Track Occupancy | 5 |  | X
| 2.2 Access Footage Archive | 3 |  |  |  | X
| 2.3 Detect Overparking | 4 |  |  |  | X
3. Parking Lot Status | 3.1 Search and Select Lot | 4 |  |  | X
| 3.2 View Occupancy | 4 |  |  | X
| 3.3 Access Occupancy Remotely | 5 |  |  | X
4. Advertising Management | 4.1 Create Ad | 2 |  | X
| 4.2 Modify Ad | 2 |  | X
| 4.3 View Ad Statistics | 3 |  | X
5. Payment gateway | 5.1 Define Payment Method | 3 | X
| 5.2 Validate Payment | 4 | X
|  | Velocity | 7 | 12 | 13 | 7

## User Story Map
Epics | User Stories | QuickFeed - User Story Map
Epic 1 - Account Management |  | Epic 1 - Account Management | Epic 2 - Parking Lot Management | Epic 3 - Parking Lot Status | Epic 4 - Advertising Management | Epic 5 - Payment Gateway | Iteration 1
Epic 2 - Parking Lot Management | [5 empty] | 5.1 Define Payment Method
Epic 3 - Parking Lot Status | [5 empty] | 5.2 Validate Payment
Epic 4 - Advertising Management |  |  | 2.1 Track Occupancy |  | 4.1 Create Ad |  | Iteration 2
Epic 5 - Payment Gateway |  |  |  |  | 4.2 Modify Ad
4.3 View Ad Statistics
|  |  |  | 3.1 Search and Select Lot |  |  | Iteration 3
3.2 View Occupancy
3.3 Access Occupancy Remotely
|  |  | 2.2 Access Footage Archive |  |  |  | Iteration 4
2.3 Detect Overparking